Table of Contents

# Sprint Planning: Medic8 Phase 1 MVP

Document ID: Medic8-SP-001 Version: 1.0 Date: 2026-04-03 Methodology: Hybrid (Water-Scrum-Fall) Phase: 1 — Foundation MVP Development Window: 16 weeks (8 sprints) plus Sprint Zero (1 week) and Post-Sprint hardening (2 weeks) Total Calendar Duration: 19 weeks Team Size: 1 (solo developer) Standards: IEEE 29148-2018, Scrum Guide 2020 Product Scope: 32 modules (Phase 1 core modules plus Module 32: AI Intelligence)

## 1 Sprint Cadence

Sprint Duration: 2 weeks (10 working days)

Ceremonies:

- Sprint Planning — Monday AM, Week 1 of sprint. Duration: 2 hours. Select stories from the prioritised backlog, confirm acceptance criteria, identify technical dependencies, and commit to the sprint goal.

- Daily Journal — Daily, 15 minutes. Solo developer replacement for the Daily Standup. Record: what was completed yesterday, what is planned today, and any blockers. Written in projects/Medic8/_context/sprint-journal.md.

- Sprint Review — Friday PM, Week 2 of sprint. Duration: 1 hour. Demonstrate completed stories against acceptance criteria on the staging environment. Record demo outcomes and stakeholder feedback.

- Sprint Retrospective — Friday PM, Week 2 of sprint (immediately after Sprint Review). Duration: 30 minutes. Document: what went well, what did not, and one actionable improvement for the next sprint.

Velocity:

- Initial estimate: 40 story points per sprint (solo developer baseline)

- Adjust after Sprint 2 based on actual throughput from Sprints 1 and 2

- Velocity range assumption: 35-50 points per sprint depending on story complexity and technical debt

Estimation Scale: Modified Fibonacci (1, 2, 3, 5, 8, 13). Any story exceeding 13 points requires decomposition before sprint commitment.

## 2 Sprint Zero: Pre-Development Foundation (1 Week)

Duration: 1 week (5 working days), preceding Sprint 1 Sprint Goal: Establish the development environment, toolchain, and foundational technical decisions so that Sprint 1 begins with zero infrastructure blockers.

| # | Task | Days | Deliverable |
| --- | --- | --- | --- |
| SZ-01 | Development environment setup: PHP 8.3, Laravel 11, Composer, Node.js, MySQL 8, Redis, Docker Compose | 1 | docker-compose.yml, .env.example, verified local stack |
| SZ-02 | Database schema design review: platform tables, auth tables, tenant isolation (facility_id pattern per BR-DATA-004) | 1 | ERD v1.0, migration stubs for auth, tenants, and global_patients |
| SZ-03 | CI/CD pipeline setup: GitHub Actions, PHPStan level 8, PHP CS Fixer (PSR-12), PHPUnit, tenant-scope CI audit rule (BR-DATA-004) | 0.5 | .github/workflows/ci.yml, passing pipeline on empty project |
| SZ-04 | Coding standards alignment: PSR-12, strict types declaration, Conventional Commits, branch naming convention, PR template | 0.5 | CONTRIBUTING.md, .php-cs-fixer.dist.php, commit-msg hook |
| SZ-05 | Test framework setup: PHPUnit 11, Pest PHP, feature test base class with tenant context, factory stubs | 0.5 | Base test classes, phpunit.xml, passing empty test suite |
| SZ-06 | Drug interaction database licensing: evaluate and licence a drug interaction dataset (DrugBank, Medi-Span, or First Databank) | 0.5 | Licensing decision documented, dataset access confirmed |
| SZ-07 | PDPA legal review initiation: engage legal counsel for Uganda Personal Data Protection Act 2019 compliance assessment | 0.5 | Legal engagement letter sent, review timeline documented |
| SZ-08 | Tabler UI template integration: install Tabler Bootstrap 5 admin template, configure Laravel Blade layout | 0.5 | Base layout with sidebar, header, and authentication views |

Exit Criteria:

- Local development environment boots in under 60 seconds

- CI pipeline runs and passes on an empty commit

- PHPStan level 8 and PHP CS Fixer are enforced in CI

- Tenant-scoped query audit rule is active in CI

- ERD v1.0 reviewed and approved

- Drug interaction data source confirmed

## 3 Phase 1 Sprint Plan

### Sprint 1: Foundation and Authentication (Weeks 1-2)

Sprint Goal: Deliver a secure, multi-tenant authentication system with tenant provisioning so that the first facility can log in and access a role-scoped dashboard.

Capacity: 38 story points

| Story ID | Story Title | Points | Priority | Dependencies |
| --- | --- | --- | --- | --- |
| US-AUTH-001 | Web Login | 5 | Critical | SZ-08 (Tabler layout) |
| US-AUTH-002 | Mobile JWT Login | 5 | Critical | -- |
| US-AUTH-003 | Token Refresh | 3 | Critical | US-AUTH-002 |
| US-AUTH-004 | Logout | 2 | Critical | US-AUTH-001, US-AUTH-002 |
| US-AUTH-005 | Session Timeout (15 min) | 3 | Critical | US-AUTH-001 |
| US-AUTH-006 | MFA for Admin Roles | 5 | High | US-AUTH-001 |
| FR-TNT-001 | Tenant Provisioning | 5 | Critical | SZ-02 (schema) |
| FR-TNT-002 | Tenant Activation/Deactivation | 3 | Critical | FR-TNT-001 |
| FR-TNT-003 | Tenant Configuration (modules, locale, currency) | 3 | High | FR-TNT-001 |
| FR-TNT-004 | Tenant Data Isolation Enforcement | 4 | Critical | FR-TNT-001, BR-DATA-004 |

Technical Tasks (not story-pointed):

- Database migrations: users, tenants, facilities, roles, permissions, personal_access_tokens, global_patients (schema only)

- Eloquent global scope for facility_id enforcement (BR-DATA-004)

- Repository base class with mandatory tenant filter

- API envelope response format

- Exception handler with typed exceptions

- Staging environment deployment

Key Risks:

- MFA TOTP library selection and testing may take longer than estimated

- Tenant isolation pattern must be validated thoroughly; a defect here propagates to every subsequent sprint

### Sprint 2: Patient Registration (Weeks 3-4)

Sprint Goal: Enable a receptionist to register new patients, look up returning patients, and manage patient identity with duplicate detection, so that the patient master index is ready for clinical workflows.

Capacity: 46 story points

| Story ID | Story Title | Points | Priority | Dependencies |
| --- | --- | --- | --- | --- |
| US-REG-001 | Register New Patient (demographics, photo) | 5 | Critical | Sprint 1 (auth, tenant) |
| US-REG-002 | Auto-Generate Unique MRN | 3 | Critical | US-REG-001 |
| US-REG-003 | Look Up Returning Patient | 5 | Critical | US-REG-001 |
| US-REG-004 | Assign Patient Category | 3 | High | US-REG-001 |
| US-REG-005 | Add Multiple Identifiers | 3 | High | US-REG-001, BR-PID-004 |
| US-REG-006 | Link Guardian for Paediatric Patient | 3 | High | US-REG-001, BR-CLIN-006 |
| US-REG-007 | Record Allergies and Chronic Conditions | 5 | Critical | US-REG-001 |
| US-REG-008 | Merge Duplicate Patient Records | 5 | High | US-REG-001, BR-PID-003 |
| US-REG-009 | EMPI Probabilistic Matching | 8 | High | US-REG-001, BR-PID-001 |
| US-REG-010 | Triage Queue Assignment | 3 | Critical | US-REG-001, BR-CLIN-001 |

Technical Tasks:

- Patient profile UI (Tabler): demographics, photo, identifiers, allergies, guardian panel

- EMPI matching algorithm: Soundex + Metaphone adapted for African naming patterns (BR-PID-001)

- Auto-save implementation for registration forms (BR-DATA-005)

- Image compression pipeline for patient photos (max 512 KB)

- global_patients table population and cross-tenant identity layer

Key Risks:

- EMPI algorithm (8 points) is the most complex story in the sprint; accuracy testing against African naming patterns requires a representative test dataset

- Sprint is at 46 points, 6 above baseline velocity; monitor daily and defer US-REG-008 (merge) if velocity target is missed

### Sprint 3: OPD Core (Weeks 5-6)

Sprint Goal: Deliver the outpatient clinical consultation workflow from queue to diagnosis, so that a doctor can see patients, record SOAP notes, enter diagnoses, and request investigations.

Capacity: 42 story points

| Story ID | Story Title | Points | Priority | Dependencies |
| --- | --- | --- | --- | --- |
| US-OPD-001 | Doctor's Queue with Triage Priority | 5 | Critical | US-REG-010 (triage queue) |
| US-OPD-002 | Triage: Vital Signs Entry | 5 | Critical | US-REG-010 |
| US-OPD-003 | Clinical Consultation: SOAP Notes | 5 | Critical | US-OPD-001 |
| US-OPD-004 | Diagnosis Entry with ICD-10 Search | 5 | Critical | US-OPD-003, BR-DATA-006 |
| US-OPD-005 | Investigation Requests (Lab, Radiology) | 5 | Critical | US-OPD-003 |
| US-OPD-006 | Clinical Notes History | 3 | High | US-OPD-003 |
| US-OPD-007 | NEWS2 Early Warning Score | 5 | High | US-OPD-002, BR-CLIN-007 |
| US-OPD-008 | Single-Page OPD Summary UI | 5 | High | US-OPD-003, US-OPD-004, US-OPD-005 |
| US-OPD-009 | Auto-Save for Clinical Forms | 4 | Critical | BR-DATA-005 |

Technical Tasks:

- ICD-10 code database import and searchable index (typeahead, min 3 characters)

- Real-time queue updates (polling or WebSocket)

- NEWS2 score calculation engine with Sub-Saharan Africa baseline adjustments (BR-CLIN-007)

- Clinical data audit trail logging (immutable append-only)

- HMIS 105 Section 1 auto-tally hooks (BR-HMIS-001)

Key Risks:

- ICD-10 dataset is large (approximately 70,000 codes); search performance must meet the 1-second response target

- NEWS2 population-adjusted thresholds require clinical validation; flag as [CONTEXT-GAP] if no validated African thresholds are available

### Sprint 4: OPD Prescribing and Clinical Decision Support (Weeks 7-8)

Sprint Goal: Deliver safe prescribing with drug interaction checking, paediatric dosing safeguards, and Five Rights CPOE enforcement, so that medication safety is embedded from the first prescription.

Capacity: 35 story points

| Story ID | Story Title | Points | Priority | Dependencies |
| --- | --- | --- | --- | --- |
| US-RX-001 | Prescription Writing (generic + brand) | 5 | Critical | US-OPD-003 |
| US-RX-002 | Stock-Aware Prescribing | 3 | High | US-RX-001, BR-RX-002 |
| US-RX-003 | Drug Interaction Checking (4-Tier Alerts) | 8 | Critical | US-RX-001, BR-CLIN-004, SZ-06 (drug DB) |
| US-RX-004 | Five Rights CPOE Enforcement | 5 | Critical | US-RX-001, BR-CLIN-008 |
| US-RX-005 | Paediatric Weight-Based Dosing | 5 | Critical | US-RX-001, BR-CLIN-006 |
| US-RX-006 | Tall Man Lettering for LASA Drugs | 3 | High | US-RX-001, BR-RX-003 |
| US-RX-007 | NEWS2 Alert Integration in Prescribing | 3 | High | US-OPD-007, US-RX-001 |
| US-RX-008 | Prescribing Authority Enforcement | 3 | Critical | US-RX-001, BR-CLIN-002 |

Technical Tasks:

- Drug formulary database schema and seed data (generic names, brands, strengths, routes, frequencies)

- CDS engine: rule evaluation pipeline for drug interactions, dosing limits, allergy cross-checks

- LASA drug list management interface for pharmacy lead

- Prescription audit trail (Tier 3 and Tier 4 override logging per BR-CLIN-004)

- CDS unit tests: positive, negative, boundary, and override scenarios (100% coverage required for CDS)

Key Risks:

- Drug interaction checking (8 points) is the highest-risk story in Phase 1; the CDS engine must fire correctly for all 4 tiers and must never silently suppress a Fatal alert

- Drug interaction database quality directly determines CDS accuracy; verify coverage of the Uganda Essential Medicines List

### Sprint 5: Laboratory (Weeks 9-10)

Sprint Goal: Deliver the laboratory workflow from sample collection to result validation, so that lab technicians can process requests, enter results with reference ranges, and trigger critical value alerts.

Capacity: 48 story points

| Story ID | Story Title | Points | Priority | Dependencies |
| --- | --- | --- | --- | --- |
| US-LAB-001 | Lab Request from Clinical Screen | 5 | Critical | US-OPD-005 |
| US-LAB-002 | Sample Collection with Barcode Generation | 5 | Critical | US-LAB-001 |
| US-LAB-003 | Specimen Tracking Workflow | 5 | High | US-LAB-002 |
| US-LAB-004 | Result Entry with Reference Ranges and Auto-Flag | 5 | Critical | US-LAB-001 |
| US-LAB-005 | Critical Value Alerts with Escalation Cascade | 8 | Critical | US-LAB-004, BR-CLIN-003 |
| US-LAB-006 | Result Validation by Supervisor | 3 | High | US-LAB-004 |
| US-LAB-007 | QC Records | 3 | High | US-LAB-004 |
| US-LAB-008 | HL7 v2 Gateway (Analyser Interface) | 8 | High | US-LAB-004 |
| US-LAB-009 | LOINC Test Definitions | 3 | High | US-LAB-001 |
| US-LAB-010 | Lab Dashboard and Turnaround Time Tracking | 3 | High | US-LAB-003 |

Technical Tasks:

- Barcode generation library integration (Code 128 for specimen labels)

- HL7 v2 message parser for analyser integration (Cobas, Mindray, Sysmex)

- LOINC test code database import

- Critical value threshold configuration per test per facility

- Escalation cascade timer service (30 min to doctor, 60 min to ward sister, then Facility Admin per BR-CLIN-003)

- HMIS 105 Section 2 auto-tally hooks (BR-HMIS-001)

Key Risks:

- Sprint is at 48 points, 8 above baseline velocity; HL7 v2 gateway (8 points) and critical value alerts (8 points) are both high-complexity stories

- If velocity is tracking below target at mid-sprint, defer US-LAB-008 (HL7 gateway) to Sprint 8 and reduce to 40 points

- HL7 v2 analyser integration requires access to test equipment or a simulator; confirm availability before sprint commitment

### Sprint 6: Pharmacy and Dispensing (Weeks 11-12)

Sprint Goal: Deliver the pharmacy dispensing workflow with stock management, so that pharmacists can dispense prescriptions, manage inventory, and track controlled substances.

Capacity: 49 story points

| Story ID | Story Title | Points | Priority | Dependencies |
| --- | --- | --- | --- | --- |
| US-PH-001 | Prescription Queue from OPD | 3 | Critical | US-RX-001 |
| US-PH-002 | Dispensing with Stock Deduction | 5 | Critical | US-PH-001 |
| US-PH-003 | Generic Substitution with Doctor Notification | 5 | High | US-PH-002, BR-CLIN-002 |
| US-PH-004 | Dispensing Label Generation | 3 | High | US-PH-002 |
| US-PH-005 | Partial Dispensing with Pending Balance | 3 | High | US-PH-002 |
| US-PH-006 | Narcotic/Controlled Drug Register | 5 | Critical | US-PH-002, BR-RX-001 |
| US-PH-007 | Stock Management: GRN, Transfer, Adjust | 5 | Critical | -- |
| US-PH-008 | Expiry Tracking (90-Day Flag) | 3 | High | US-PH-007 |
| US-PH-009 | Minimum Stock Level Alerts | 3 | High | US-PH-007 |
| US-PH-010 | Drug Formulary Management | 5 | High | US-PH-007 |
| US-PH-011 | Medication Reconciliation | 5 | Critical | US-PH-002, BR-CLIN-005 |
| US-PH-012 | Stock Valuation (FIFO) | 4 | High | US-PH-007 |

Technical Tasks:

- Pharmacy dispensing UI with prescription preview, stock levels, and substitution workflow

- Stock movement ledger: GRN, transfer, adjustment with full audit trail

- Barcode scanning for drug packs during GRN

- Narcotic register with running balance and discrepancy alerting (BR-RX-001)

- Expiry date batch tracking and 90-day warning report

- Medication reconciliation form generation at care transitions (BR-CLIN-005)

Key Risks:

- Sprint is at 49 points, the highest in Phase 1; this reflects the breadth of pharmacy operations

- If velocity is tracking below target, defer US-PH-012 (stock valuation) and US-PH-010 (formulary management) to Sprint 8, reducing to 40 points

- Narcotic register accuracy is a regulatory requirement; testing must include physical count reconciliation scenarios

### Sprint 7: Billing, Payments, and Appointments (Weeks 13-14)

Sprint Goal: Deliver cash billing, mobile money payments, and appointment scheduling, so that the facility can collect revenue, reconcile daily cash, and manage patient appointments.

Capacity: 39 story points

| Story ID | Story Title | Points | Priority | Dependencies |
| --- | --- | --- | --- | --- |
| US-BIL-001 | Patient Account with Real-Time Charge Accumulation | 5 | Critical | US-OPD-003, BR-FIN-001 |
| US-BIL-002 | Auto-Billing from Clinical Screens | 5 | Critical | US-BIL-001, BR-FIN-001 |
| US-BIL-003 | Configurable Price List and Category Pricing | 3 | Critical | US-BIL-001 |
| US-BIL-004 | Cash Payment and Receipt Generation | 3 | Critical | US-BIL-001 |
| US-BIL-005 | Mobile Money Integration (MTN MoMo / Airtel Money) | 5 | High | US-BIL-001, BR-FIN-003 |
| US-BIL-006 | Daily Cashier Reconciliation | 3 | High | US-BIL-004, BR-FIN-004 |
| US-BIL-007 | Missing Charge Detection | 3 | High | US-BIL-002, BR-FIN-008 |
| US-APT-001 | Appointment Booking | 5 | High | Sprint 1 (auth) |
| US-APT-002 | SMS Appointment Reminders | 3 | High | US-APT-001 |
| US-APT-003 | Queue Integration from Appointments | 4 | High | US-APT-001, US-OPD-001 |

Technical Tasks:

- Billing engine: charge accumulation from lab, pharmacy, OPD, and procedure events

- Price list management UI with category-based pricing tiers

- Receipt generation (thermal printer and PDF)

- MTN MoMo API and Airtel Money API integration with webhook handlers

- Unmatched payment suspense account and daily report (BR-FIN-003)

- Cashier session management: open, close, reconcile (BR-FIN-004)

- SMS gateway integration (Africa's Talking API) for appointment reminders

- Appointment calendar UI with doctor availability and walk-in slot management

Key Risks:

- Mobile money API integration depends on MTN and Airtel developer portal access and sandbox availability; initiate API credentials request in Sprint 6

- SMS gateway requires Africa's Talking account and sender ID registration; initiate in Sprint 6

### Sprint 8: RBAC, Integration Testing, and Hardening (Weeks 15-16)

Sprint Goal: Deliver role-based access control with 18 default roles, emergency access, and a comprehensive audit trail. Complete end-to-end integration testing, performance testing, and security hardening so that the system is ready for UAT.

Capacity: 31 story points

| Story ID | Story Title | Points | Priority | Dependencies |
| --- | --- | --- | --- | --- |
| US-RBAC-001 | 18 Default Roles with Permission Matrix | 5 | Critical | Sprint 1 (auth) |
| US-RBAC-002 | Custom Role Creation | 3 | High | US-RBAC-001 |
| US-RBAC-003 | ABAC for Sensitive Records (HIV, psychiatric) | 5 | Critical | US-RBAC-001 |
| US-RBAC-004 | Audit Trail (Immutable) | 5 | Critical | BR-DATA-004, PDPA 2019 Section 24 |
| US-RBAC-005 | Emergency Access (Break-the-Glass) | 5 | Critical | US-RBAC-001, BR-DATA-002 |
| US-RBAC-006 | Role-Scoped Dashboard | 3 | High | US-RBAC-001 |
| US-INT-001 | End-to-End Integration Test Suite | 5 | Critical | All Sprint 1-7 stories |

Technical Tasks (non-story-pointed, Sprint 8 dedicated):

- End-to-end integration tests: patient journey from registration through OPD, lab, pharmacy, billing, and discharge

- Performance testing: confirm P95 API response time under 500 ms with 50 concurrent users per facility

- Security hardening: composer audit, OWASP dependency check, HTTP security headers, rate limiting

- Bug fixes from Sprints 1-7 (reserve 20% of capacity = approximately 6 points equivalent)

- Audit trail tamper-proof implementation: append-only log table with hash chain

- ABAC policy engine for sensitive record types (HIV status, psychiatric notes)

- Break-the-glass workflow: emergency access with 2-factor patient confirmation, 24-hour expiry, SMS notification (BR-DATA-002)

- DOCUMENTATION-STATUS.md update for all Phase 1 modules

Key Risks:

- Integration testing may uncover cross-module defects that require fixes in earlier module code; reserve capacity for rework

- Performance testing requires a representative data set; generate synthetic data (at least 10,000 patients, 50,000 encounters) during Sprint 7

## 4 Post-Sprint 8: UAT and Go-Live Preparation (2 Weeks)

Duration: 2 weeks (Weeks 17-18) Purpose: Validate the system with real users at pilot facilities before production go-live.

### Week 17: User Acceptance Testing

| # | Activity | Duration | Participants |
| --- | --- | --- | --- |
| PS-01 | Deploy to UAT environment with synthetic data | 1 day | Developer |
| PS-02 | UAT with Pilot Facility 1: private clinic (small, OPD-focused) | 2 days | Receptionist, Doctor, Pharmacist, Cashier |
| PS-03 | UAT with Pilot Facility 2: mission hospital (multi-department) | 2 days | Lab Technician, Nurse, Facility Admin |

### Week 18: Stabilisation and Go-Live

| # | Activity | Duration | Participants |
| --- | --- | --- | --- |
| PS-04 | UAT with Pilot Facility 3: HC IV (HMIS reporting focus) | 1 day | Records Officer, Facility Admin |
| PS-05 | Bug fixes from UAT findings | 2 days | Developer |
| PS-06 | Performance optimisation based on UAT load patterns | 1 day | Developer |
| PS-07 | Go-live preparation: production environment, DNS, SSL, backups, monitoring | 1 day | Developer |

UAT Exit Criteria:

- All Critical and High priority bugs fixed

- 3 pilot facilities have signed UAT acceptance

- End-to-end patient journey completed successfully at each facility

- Cash billing reconciliation rate at 95% or above (Phase 1 success criterion)

- P95 API response time under 500 ms confirmed under UAT load

- CDS rules validated: drug interaction alerts fire at correct severity tier

- Clinical safety sign-off from clinical advisor

- Data backup and restore procedure tested

- Rollback procedure documented and tested

## 5 Sprint Point Summary

| Sprint | Name | Points | Cumulative |
| --- | --- | --- | --- |
| 0 | Pre-Development Foundation | -- | -- |
| 1 | Foundation and Authentication | 38 | 38 |
| 2 | Patient Registration | 46 | 84 |
| 3 | OPD Core | 42 | 126 |
| 4 | OPD Prescribing and CDS | 35 | 161 |
| 5 | Laboratory | 48 | 209 |
| 6 | Pharmacy and Dispensing | 49 | 258 |
| 7 | Billing, Payments, and Appointments | 39 | 297 |
| 8 | RBAC, Integration, and Hardening | 31 | 328 |
| Total |  | 328 |  |

Average velocity required: 41 points per sprint (328 / 8 sprints)

## 6 Dependency Chain

The following critical path dependencies must be completed in sequence. Delays on any critical path item cascade to all downstream sprints.

Sprint 0: Environment + Schema + CI
    |
Sprint 1: Auth + Tenant Isolation
    |
    +---> Sprint 2: Patient Registration + EMPI
    |         |
    |         +---> Sprint 3: OPD Core (Queue, Triage, SOAP, ICD-10, Investigations)
    |                   |
    |                   +---> Sprint 4: Prescribing + CDS Engine
    |                   |         |
    |                   |         +---> Sprint 6: Pharmacy Dispensing + Stock
    |                   |
    |                   +---> Sprint 5: Laboratory (requests flow from OPD)
    |
    +---> Sprint 7: Billing (charges from OPD, Lab, Pharmacy) + Appointments
    |
    +---> Sprint 8: RBAC + Integration Testing + Hardening

## 7 Risk Register (Sprint-Level)

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| Solo developer illness or unavailability (1+ week) | Medium | High | Maintain Sprint Journal for continuity; all work in version control with Conventional Commits |
| Drug interaction database licensing delay | Low | Critical | Initiate in Sprint Zero; fallback to open-source interaction dataset (reduced coverage) |
| Mobile money API sandbox unavailability | Medium | Medium | Start API credential requests in Sprint 6; fallback to manual payment entry with MoMo reference |
| Sprint 5 and 6 exceed velocity (48 and 49 points) | High | Medium | Pre-identify deferral candidates: US-LAB-008, US-PH-012, US-PH-010; move to Sprint 8 if needed |
| HL7 analyser integration requires physical equipment | Medium | Medium | Use HL7 simulator for development and testing; defer physical analyser testing to UAT |
| EMPI accuracy for African naming patterns | Medium | High | Build representative test dataset with compound surnames, clan names, and spelling variations |
| Performance target miss at 50 concurrent users | Low | High | Run load tests from Sprint 5 onward; optimise database queries and add caching incrementally |

## Module 32: AI Intelligence

Module 32 (AI Intelligence) is provider-agnostic and supports OpenAI, Anthropic, DeepSeek, and Gemini via a shared AIProviderInterface. It exposes 6 capabilities: Clinical Documentation, ICD Coding Assist, Differential Diagnosis, Patient Plain-Language Summary, Claim Scrubbing, and Outbreak Alert. Billing is either credit_pack or flat_fee per tenant configuration.

AI Intelligence stories require sandbox API keys for the target provider to be configured in .env.testing before sprint planning can accept those stories as ready. Stories that arrive at Sprint Planning without confirmed sandbox access cannot be committed to the sprint.

## 8 Definition Cross-References

- Definition of Done: 07-agile-artifacts/02-dod/01-definition-of-done.md

- Definition of Ready: 07-agile-artifacts/03-dor/01-definition-of-ready.md

- User Stories: 02-requirements-engineering/02-user-stories/01-user-stories.md

- Business Rules: _context/business_rules.md

- Quality Standards: _context/quality_standards.md

- Metrics and Phase Gates: _context/metrics.md