Table of Contents

# Sprint Planning — AcademiaPro Phase 1

## Document Control

| Field | Value |
| --- | --- |
| Project | AcademiaPro |
| Phase | Phase 1 — Core Web Application |
| Methodology | Hybrid (Water-Scrum-Fall) |
| Sprint Duration | 2 weeks (10 working days) |
| Team Size | 1 (solo developer — Peter, Chwezi Core Systems) |
| Total FRs in Scope | 49 (FR-AUTH through FR-AUD) |
| Planned Sprints | Sprint Zero + Sprints 1 through 8 + Post-Sprint 8 UAT |
| Estimated Duration | 18 weeks (Sprint Zero: 1 week; Sprints 1–8: 16 weeks; UAT: 1+ weeks) |

## Sprint Cadence and Ceremonies

| Ceremony | Frequency | Duration | Participants |
| --- | --- | --- | --- |
| Sprint Planning | Day 1 of each sprint | 1 hour | Peter (dev) |
| Daily Stand-up Log | Daily | 10-minute written log in docs/standups/ | Peter |
| Sprint Review / Demo | Last day of each sprint | 30 minutes recorded screen demo | Peter |
| Sprint Retrospective | Last day of each sprint | 15-minute written retro in docs/retros/ | Peter |
| Phase Gate Review | After Sprint 8 + UAT | Formal sign-off against Phase 1 gate criteria | Peter |

Solo developer adaptation: ceremonies are written logs and screen recordings rather than meetings. The discipline of documenting each ceremony is preserved to maintain audit traceability per the Water-Scrum-Fall methodology.

## Velocity Assumptions

| Parameter | Value | Rationale |
| --- | --- | --- |
| Story points per sprint | 20–25 SP | Solo developer, 2-week sprints, estimated from complexity not hours |
| Sprint Zero capacity | 10–12 SP | 1-week sprint; infrastructure tasks carry high uncertainty |
| Buffer allocation | Sprint 8 is 100% buffer | No new features; integration testing, performance testing, bug fixes |
| Total story points (Phase 1) | ~180 SP estimated | 49 FRs across 8 feature sprints |

## Sprint Zero — Foundation (1 Week)

Goal: Establish the development environment, database schema, CI/CD pipeline, and UI framework so that Sprint 1 begins with zero infrastructure blockers.

Duration: 1 week (5 working days).

| Task ID | Task | Story Points | Acceptance Criteria |
| --- | --- | --- | --- |
| S0-001 | Initialise Laravel 11 project with PHP 8.2+ | 2 | php artisan serve returns HTTP 200; PSR-12 enforced via PHP CS Fixer |
| S0-002 | Configure MySQL 8.x database with strict mode, utf8mb4, InnoDB | 1 | SHOW VARIABLES LIKE 'sql_mode' returns strict mode; SHOW CREATE DATABASE shows utf8mb4 |
| S0-003 | Run baseline migrations: tenants, tbl_users, tbl_audit_log | 2 | php artisan migrate succeeds; tables exist with tenant_id columns where applicable |
| S0-004 | Configure Redis 7 for cache and queue drivers | 1 | php artisan queue:work processes a test job; Cache::put() / Cache::get() round-trips |
| S0-005 | Set up GitHub Actions CI pipeline: lint, PHPStan level 8, PHPUnit | 3 | Push to main triggers pipeline; pipeline passes with zero errors |
| S0-006 | Install React 18 / TypeScript / Vite frontend scaffold | 2 | npm run dev serves the Vite dev server; TypeScript compilation succeeds |
| S0-007 | Install shadcn/ui + Tailwind CSS; configure Tabler dashboard layout | 2 | Login page renders with shadcn/ui components; Tailwind classes apply correctly |
| S0-008 | Seed Super Admin user and default Uganda tenant for development | 1 | php artisan db:seed creates 1 Super Admin user and 1 tenant with status = active |

Total: ~14 SP (1 week).

Sprint Zero Exit Criteria:

- Laravel project boots and serves HTTP 200

- MySQL strict mode confirmed

- CI pipeline green on push to main

- Frontend dev server renders the Tabler dashboard shell

- Super Admin can log in to a blank dashboard (no module functionality yet)

## Sprint 1 — Authentication and Tenant Management (2 Weeks)

Goal: Deliver secure authentication (web + API) and Super Admin tenant lifecycle management so that all subsequent sprints operate within a multi-tenant, role-scoped context.

FR Scope: FR-AUTH-001 through FR-AUTH-006 (6 FRs) + FR-TNT-001 through FR-TNT-003 (3 FRs) = 9 FRs.

| FR ID | Description | Story Points | Dependencies |
| --- | --- | --- | --- |
| FR-AUTH-001 | Web session login (Argon2ID, CSRF, account lock after 5 failures) | 5 | S0-003 (users table) |
| FR-AUTH-002 | API / mobile JWT login (access + refresh tokens, device tracking) | 5 | FR-AUTH-001 |
| FR-AUTH-003 | JWT token refresh with rotation and revocation | 3 | FR-AUTH-002 |
| FR-AUTH-004 | Session logout (web + API) | 2 | FR-AUTH-001, FR-AUTH-002 |
| FR-AUTH-005 | Idle session timeout (30 minutes) | 2 | FR-AUTH-001 |
| FR-AUTH-006 | Super Admin MFA (TOTP) | 3 | FR-AUTH-001 |
| FR-TNT-001 | Tenant provisioning (create school, owner account, welcome email) | 3 | FR-AUTH-001 |
| FR-TNT-002 | Tenant activation (pending to active) | 2 | FR-TNT-001 |
| FR-TNT-003 | Tenant suspension | 2 | FR-TNT-001 |

Total: ~27 SP.

Key Deliverables:

- Login page (web) with lockout behaviour

- JWT endpoint for mobile/API clients

- Token refresh and revocation

- MFA challenge for Super Admin panel

- Tenant CRUD in Super Admin panel

- Welcome email on tenant creation

- Tenant status transitions: pending, active, suspended

Sprint 1 Exit Criteria:

- All 6 FR-AUTH acceptance criteria pass (Playwright + PHPUnit)

- All 3 FR-TNT acceptance criteria pass

- JWT tokens decode with correct tenant_id claim

- Account lockout triggers after 5 failed attempts

- Super Admin MFA blocks dashboard access until TOTP verified

- CI pipeline green

## Sprint 2 — Student Information System (2 Weeks)

Goal: Deliver the full student lifecycle — admission, enrollment, cross-school lookup, transfer, and retention lock — establishing the global student identity architecture.

FR Scope: FR-SIS-001 through FR-SIS-005 (5 FRs).

| FR ID | Description | Story Points | Dependencies |
| --- | --- | --- | --- |
| FR-SIS-001 | Student admission (40+ fields, NIN/LIN, passport photo upload) | 8 | Sprint 1 (auth, tenant context) |
| FR-SIS-002 | Cross-school enrollment via NIN/LIN lookup | 5 | FR-SIS-001, BR-STU-001 through BR-STU-004 |
| FR-SIS-003 | Student search (Meilisearch integration) | 3 | FR-SIS-001 |
| FR-SIS-004 | Transfer out (departure record, reason code, read-only lock) | 3 | FR-SIS-001, BR-DEPART-001 through BR-DEPART-004 |
| FR-SIS-005 | Retention lock (prevent deletion of enrolled student) | 2 | FR-SIS-001 |

Total: ~21 SP.

Key Deliverables:

- Student admission form (40+ fields with validation)

- global_students and school_enrollments table separation

- NIN/LIN cross-school lookup (no duplicate UIDs)

- Meilisearch-powered student search

- Transfer-out workflow with departure reason codes

- Student record immutability after departure

Sprint 2 Exit Criteria:

- Student admission creates both global_students and school_enrollments records

- NIN/LIN lookup returns existing global student without duplication (BR-STU-001)

- Single-school active enrollment enforced (BR-STU-004)

- Departed student records are read-only (BR-DEPART-004)

- Meilisearch index returns results within 200 ms (P99)

- CI pipeline green

## Sprint 3 — Academics Setup (2 Weeks)

Goal: Define the school structure — academic years, terms, classes/streams, subjects, curricula, and timetables — so that downstream modules (Fees, Attendance, Examinations) can reference a configured academic context.

FR Scope: FR-ACA-001 through FR-ACA-004 (4 FRs).

| FR ID | Description | Story Points | Dependencies |
| --- | --- | --- | --- |
| FR-ACA-001 | Academic year lifecycle (create, open, close, promotion wizard) | 5 | Sprint 1 (tenant), BR-PROM-001 through BR-PROM-007 |
| FR-ACA-002 | Class and stream management (promotes-to config) | 3 | FR-ACA-001 |
| FR-ACA-003 | Curriculum type configuration (Thematic P1–P3, standard P4–P7, O-Level, A-Level) | 3 | FR-ACA-002 |
| FR-ACA-004 | Timetable builder (per class per term) | 5 | FR-ACA-002, FR-ACA-003 |

Total: ~16 SP.

Key Deliverables:

- Academic year CRUD with term dates (3-term Uganda calendar)

- Year-Start Promotion Wizard (BR-PROM-001 through BR-PROM-007)

- Class/stream CRUD with "Promotes To" configuration

- Curriculum type selector per class level

- Timetable grid builder (days x periods)

Sprint 3 Exit Criteria:

- Academic year creates 3 terms automatically (BR-CAL-001)

- Promotion wizard blocks Term 1 opening until all classes processed (BR-PROM-001)

- Final-year classes (P7, S.4, S.6) have promotes_to = null (BR-PROM-002)

- Curriculum type determines available grading scales

- Timetable renders correctly for a class with 8 periods per day

- CI pipeline green

## Sprint 4 — Fee Management and SchoolPay Integration (2 Weeks)

Goal: Deliver term-based fee billing, manual payment recording, receipt generation, fee reminders, refund workflow, and the SchoolPay webhook integration for automated payment sync.

FR Scope: FR-FEE-001 through FR-FEE-007 (7 FRs).

| FR ID | Description | Story Points | Dependencies |
| --- | --- | --- | --- |
| FR-FEE-001 | Fee structure definition (per class, per term, UGX) | 3 | Sprint 3 (academic year, classes) |
| FR-FEE-002 | Manual payment recording (cash/bank, partial payments, KUPAA model) | 5 | FR-FEE-001, BR-FEE-002, BR-FEE-005 |
| FR-FEE-003 | Auto-generated sequential receipts | 3 | FR-FEE-002, BR-FEE-004 |
| FR-FEE-004 | Fee reminders (D-7, D-1, D+7 auto-send via SMS) | 3 | FR-FEE-001, BR-FEE-006 |
| FR-FEE-005 | Refund workflow (bursar initiate, owner approve) | 3 | FR-FEE-002, BR-FEE-007 |
| FR-FEE-006 | Fee balance tracking and arrears carry-forward | 2 | FR-FEE-001, BR-FEE-003 |
| FR-FEE-007 | Financial reports (collection summary, defaulters, term reconciliation) | 3 | FR-FEE-002 |

Total: ~22 SP.

SchoolPay Integration Tasks (bundled with FR-FEE scope):

| Task ID | Task | Story Points |
| --- | --- | --- |
| SP-001 | SchoolPay API client service (student payment codes) | 3 |
| SP-002 | Webhook receiver for payment notifications | 3 |
| SP-003 | Nightly reconciliation polling job | 2 |
| SP-004 | Double-payment prevention (5-minute window, BR-FEE-005) | 2 |

SchoolPay Total: ~10 SP.

Combined Sprint 4 Total: ~32 SP. This sprint is overloaded by ~7–12 SP. Mitigation: SchoolPay integration tasks SP-003 and SP-004 may spill into Sprint 5 if velocity is below 25 SP. The manual fee workflow (FR-FEE-001 through FR-FEE-007) is the priority; SchoolPay auto-sync is secondary.

Sprint 4 Exit Criteria:

- Fee structure created for a class/term in UGX

- Partial payment accepted with zero minimum floor (BR-FEE-002)

- Receipt auto-generated with sequential number (BR-FEE-004)

- Duplicate payment within 5-minute window rejected (BR-FEE-005)

- Refund requires owner approval (BR-FEE-007)

- Fee reminders fire at D-7, D-1, D+7 (configurable, BR-FEE-006)

- SchoolPay webhook processes a test payment notification

- Financial reports generate correctly for a test dataset

- CI pipeline green

## Sprint 5 — Attendance and Examinations Core (2 Weeks)

Goal: Deliver daily attendance entry with parent alerts, and lay the examination foundation — exam configuration, mark entry, and the mark-unlock workflow.

FR Scope: FR-ATT-001 through FR-ATT-004 (4 FRs) + FR-EXM-001, FR-EXM-002, FR-EXM-003 (3 FRs) = 7 FRs.

| FR ID | Description | Story Points | Dependencies |
| --- | --- | --- | --- |
| FR-ATT-001 | Daily attendance entry (Present/Absent/Late/Excused) | 3 | Sprint 2 (students), Sprint 3 (classes) |
| FR-ATT-002 | Absence alert (auto-SMS after N consecutive absences) | 3 | FR-ATT-001, BR-ATT-002 |
| FR-ATT-003 | Attendance amendment (48-hour teacher window, Head Teacher override) | 3 | FR-ATT-001, BR-ATT-003 |
| FR-ATT-004 | Monthly attendance report | 2 | FR-ATT-001 |
| FR-EXM-001 | Exam configuration (exam type, subjects, max marks) | 3 | Sprint 3 (curriculum type) |
| FR-EXM-002 | Mark entry (per student per subject, out-of-range rejection) | 5 | FR-EXM-001, BR-UNEB-005 |
| FR-EXM-003 | Mark unlock workflow (teacher request, Head Teacher approval) | 3 | FR-EXM-002 |

Total: ~22 SP.

Key Deliverables:

- Attendance entry grid (class view, one-click per student)

- Auto-SMS to parent after 3 consecutive absences (Africa's Talking)

- Attendance amendment audit trail

- Monthly attendance summary report

- Exam configuration CRUD

- Mark entry sheet with real-time validation (reject marks > max)

- Mark-unlock request/approval workflow

Sprint 5 Exit Criteria:

- Attendance recorded for a class of 50 students within 2 minutes

- 3 consecutive absences trigger SMS to parent/guardian (BR-ATT-002)

- Amendment after 48 hours requires Head Teacher role (BR-ATT-003)

- Marks exceeding configured maximum are rejected at API layer (BR-UNEB-005)

- Mark-unlock requires Head Teacher approval

- CI pipeline green

## Sprint 6 — Examinations Grading and Report Cards (2 Weeks)

Goal: Deliver the UNEB grading engine for all 4 curriculum types and auto-generated report cards, completing the academic cycle from mark entry to printed report.

FR Scope: FR-EXM-004 through FR-EXM-008 (5 FRs) + FR-RPT-001 through FR-RPT-004 (4 FRs) = 9 FRs.

| FR ID | Description | Story Points | Dependencies |
| --- | --- | --- | --- |
| FR-EXM-004 | PLE grading engine (4-subject aggregate, divisions) | 3 | FR-EXM-002, BR-UNEB-001 |
| FR-EXM-005 | UCE O-Level grading engine (D1–F9, aggregate divisions) | 3 | FR-EXM-002, BR-UNEB-002 |
| FR-EXM-006 | UACE A-Level grading engine (principal/subsidiary points) | 3 | FR-EXM-002, BR-UNEB-003 |
| FR-EXM-007 | Thematic Curriculum grading (P1–P3, HC/C/NYC descriptors) | 2 | FR-EXM-002, BR-UNEB-004 |
| FR-EXM-008 | UNEB exam registration data export | 2 | FR-EXM-004 through FR-EXM-006 |
| FR-RPT-001 | Single student report card (auto-generated, PDF export) | 5 | FR-EXM-004 through FR-EXM-007 |
| FR-RPT-002 | Bulk report card generation (entire class) | 3 | FR-RPT-001 |
| FR-RPT-003 | School-level performance summary | 2 | FR-EXM-004 through FR-EXM-007 |
| FR-RPT-004 | Head Teacher comments on report cards | 1 | FR-RPT-001 |

Total: ~24 SP.

Key Deliverables:

- UNEB grading engine: PLE, UCE, UACE, Thematic (4 algorithms)

- Grade computation unit tests with 100% coverage against UNEB rules

- UNEB export file generation

- Single student report card (PDF) with grades, comments, school logo

- Bulk report card generation (200 students within 120 seconds per quality target)

- School performance summary dashboard

- Head Teacher comment entry per student

Sprint 6 Exit Criteria:

- PLE aggregate computation matches BR-UNEB-001 division boundaries exactly

- UCE aggregate computation matches BR-UNEB-002 division boundaries exactly

- UACE points computation matches BR-UNEB-003 rules exactly

- Thematic grading returns HC/C/NYC descriptors only (BR-UNEB-004)

- 100% unit test coverage on all 4 grading algorithms

- Single report card generates within 3,000 ms (quality target)

- Bulk generation of 200 report cards completes within 120 seconds

- UNEB export file validates against expected format

- CI pipeline green

## Sprint 7 — RBAC, EMIS Export, and Audit Trail (2 Weeks)

Goal: Deliver the full RBAC permission system, the MoES/EMIS government data export, and the immutable audit trail — closing all remaining Phase 1 functional requirements.

FR Scope: FR-RBAC-001 through FR-RBAC-005 (5 FRs) + FR-EMIS-001 (1 FR) + FR-AUD-001 (1 FR) = 7 FRs.

| FR ID | Description | Story Points | Dependencies |
| --- | --- | --- | --- |
| FR-RBAC-001 | Permission resolution engine (role + custom overrides) | 5 | Sprint 1 (users, tenant) |
| FR-RBAC-002 | Role assignment per school per user | 3 | FR-RBAC-001, BR-RBAC-001 |
| FR-RBAC-003 | User invitation workflow (email invite, role pre-assignment) | 3 | FR-RBAC-002 |
| FR-RBAC-004 | Session expiry enforcement by role | 2 | FR-AUTH-005, FR-RBAC-001 |
| FR-RBAC-005 | Super Admin cross-tenant audit logging | 2 | FR-RBAC-001, BR-MT-003 |
| FR-EMIS-001 | EMIS government export (MoES-specified format) | 3 | Sprint 2 (students), Sprint 3 (academics) |
| FR-AUD-001 | Immutable audit trail (create/update/delete on all sensitive entities) | 5 | All prior sprints |

Total: ~23 SP.

Key Deliverables:

- Permission resolution: 60+ permissions x 8 standard roles (per RBAC matrix)

- Custom role creation per school

- User invitation email with role pre-assignment

- Role-scoped session timeout rules

- Super Admin cross-tenant read logging (BR-MT-003)

- EMIS bulk export in MoES-specified format (XML/CSV)

- Immutable audit log: user_id, tenant_id, timestamp, before/after values on all student, fee, and health records

Sprint 7 Exit Criteria:

- Permission resolution returns correct allow/deny for all 60+ permissions per role

- No user can assign a role with higher privilege than their own (BR-RBAC-002)

- Invited user receives email and can register with pre-assigned role

- Super Admin cross-tenant reads are logged with access reason (BR-MT-003)

- EMIS export generates valid file for a school with 500 students

- Audit log captures before/after values for all create/update/delete operations

- Audit log records are append-only (no update/delete permitted on tbl_audit_log)

- CI pipeline green

## Sprint 8 — Integration Testing, Performance Testing, and Hardening (2 Weeks)

Goal: No new features. Conduct end-to-end integration testing across all 49 FRs, performance testing against quality targets, security hardening, and bug fixes.

FR Scope: 0 new FRs. All 49 existing FRs under regression testing.

| Task ID | Task | Story Points | Acceptance Criteria |
| --- | --- | --- | --- |
| S8-001 | End-to-end integration test suite (Playwright): admission through report card | 5 | All critical user flows pass |
| S8-002 | Performance testing (k6): API P95 ≤ 500 ms under 200 concurrent requests | 3 | k6 report shows P95 ≤ 500 ms for all CRUD endpoints |
| S8-003 | Bulk report card load test: 200 students within 120 seconds | 2 | Timed test passes |
| S8-004 | UNEB grading accuracy test: 500 students within 5 seconds | 2 | PHPUnit timed test passes |
| S8-005 | Security audit: OWASP Top 10 scan, tenant isolation verification | 3 | Zero critical or high findings |
| S8-006 | Multi-tenant isolation test: tenant A cannot access tenant B data | 3 | Cross-tenant query returns 0 records for all endpoints |
| S8-007 | Bug fix backlog (accumulated from Sprints 1–7) | 5 | All P1/P2 bugs resolved |
| S8-008 | CI/CD pipeline for staging environment deployment | 2 | Push to staging branch deploys to staging server |

Total: ~25 SP.

Sprint 8 Exit Criteria:

- All 49 FRs have passing automated tests (PHPUnit + Playwright)

- Backend test coverage ≥ 80% line coverage

- UNEB grading engine test coverage = 100%

- Fee calculation logic test coverage = 100%

- API P95 response time ≤ 500 ms (k6 report)

- Bulk report card generation ≤ 120 seconds for 200 students

- Zero critical or high OWASP findings

- Zero P1/P2 open bugs

- Staging environment deployed and accessible

- CI pipeline green

## Post-Sprint 8 — User Acceptance Testing (1+ Weeks)

Goal: Conduct UAT with 3 pilot schools to validate real-world usability before Phase 1 sign-off.

| Task ID | Task | Duration | Acceptance Criteria |
| --- | --- | --- | --- |
| UAT-001 | Pilot school onboarding (3 schools: 1 primary, 1 secondary, 1 mixed) | 2 days | All 3 schools have active tenants with real data seeded |
| UAT-002 | Guided UAT sessions: admission, fee payment, attendance, mark entry, report card | 3 days | Each school completes the full workflow without system errors |
| UAT-003 | Bug triage and hot-fix cycle | 2 days | All UAT-discovered P1 bugs fixed and re-tested |
| UAT-004 | UNEB grading validation with real mark sheets | 1 day | Grades match manual computation for all 4 curriculum types |
| UAT-005 | Phase 1 gate sign-off | 1 day | Peter signs off Phase 1 gate criteria (see _context/metrics.md) |

UAT Exit Criteria:

- At least 1 pilot school is live on production (Phase 1 gate requirement)

- All P1/P2 bugs from UAT resolved

- UNEB grading accuracy confirmed against sample mark sheets

- SchoolPay test transaction confirmed (if SchoolPay merchant onboarding is complete)

- Phase 1 gate criteria in _context/metrics.md all met

## Sprint Allocation Summary

| Sprint | Duration | FR Groups | FR Count | Estimated SP |
| --- | --- | --- | --- | --- |
| Sprint Zero | 1 week | Infrastructure | 0 | 14 |
| Sprint 1 | 2 weeks | FR-AUTH, FR-TNT | 9 | 27 |
| Sprint 2 | 2 weeks | FR-SIS | 5 | 21 |
| Sprint 3 | 2 weeks | FR-ACA | 4 | 16 |
| Sprint 4 | 2 weeks | FR-FEE + SchoolPay | 7 | 32 |
| Sprint 5 | 2 weeks | FR-ATT, FR-EXM (core) | 7 | 22 |
| Sprint 6 | 2 weeks | FR-EXM (grading), FR-RPT | 9 | 24 |
| Sprint 7 | 2 weeks | FR-RBAC, FR-EMIS, FR-AUD | 7 | 23 |
| Sprint 8 | 2 weeks | Hardening (no new FRs) | 0 | 25 |
| UAT | 1+ weeks | Validation | 0 | — |
| Total | 18 weeks |  | 49 (unique) | ~204 |

## Risk Register (Sprint-Level)

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Sprint 4 overloaded (FR-FEE + SchoolPay) | High | Medium | SchoolPay reconciliation tasks spill to Sprint 5; manual fees are priority |
| SchoolPay merchant onboarding delayed | Medium | High | Manual fee workflow is fully functional without SchoolPay; integration is additive |
| UNEB grading rules ambiguous without official UNEB manual | Medium | High | Peter contacts UNEB for grading manual before Sprint 6 (see external actions in README) |
| EMIS export format unavailable from MoES | Medium | Medium | Generate best-effort export based on available MoES documentation; validate post-launch |
| Solo developer illness/unavailability | Low | High | Sprint 8 buffer absorbs 1-sprint delay; all work is in version control |
| Performance targets missed on budget hardware | Medium | Medium | Optimise queries in Sprint 8; defer to AWS EC2 scaling in Phase 8 if needed |

## Cross-References

| Reference | Location |
| --- | --- |
| Functional Requirements (49 FRs) | 02-requirements-engineering/01-srs/04-functional-requirements.md |
| User Stories (20 stories) | 02-requirements-engineering/02-user-stories/01-user-stories.md |
| RBAC Permission Matrix | 02-requirements-engineering/03-stakeholder-analysis/01-rbac-matrix.md |
| Business Rules | _context/business_rules.md |
| Quality Standards (performance targets) | _context/quality_standards.md |
| Technology Stack | _context/tech_stack.md |
| Phase Gate Criteria | _context/metrics.md |
| Definition of Done | 07-agile-artifacts/02-dod/01-definition-of-done.md |
| Definition of Ready | 07-agile-artifacts/03-dor/01-definition-of-ready.md |